## Sheet1
ID | Story Title | Depends On | Points | Priority | As a/an [user type] | I want [functionality] | So that [value] | NFR | Definition of Done | Epic ID | Notes | Status
Legend
Main Game Stories
Admin Stories
Friend Stories
Login / Menu Stories
*** When a player gets a full set of a card, this should be a automatic function that removes that set from the users deck and leaves it face down on the table (This lets all players know that set is now taken out of the total deck of cards ***
*** Win condition - once all cards are played (all sets are placed on the table), check which user has the most completed sets. This is also a automatic function used to evaluate the winner. We can probably implement a nice loading screen animation to allow the program to have suspense when announcing the winner ***
Accepted Stories
S2 | Joining as Guest |  | 2 | Medium | Player | to be able to join for ONE session | I can still play with my friends until i log out | Usability | I can join for one session to play any amount of Go Fish games | 0 | Silas | Closed
S3 | Logging in/out | S1 | 3 | High | Player | to be prompted to either create a new account or log into a pre existing account (Email or Google Auth for now) | I can have security in my account and save my prior progress made | Usability | I can create an account or log into a prior account | 0 | Silas - | Closed
S7 | Adding a Friend |  | 2 | High | Player | to be able to enter the username of the friend i want to add | I can have easier access to them (messaging, inviting, etc) | Usability | The invitiation is sent to the friend / after accepting, they are added to list | 0 | Ryland | Open
S11 | Friend Editing - send VC | S7 | 3 | Low | Player | to be able to send my friends currency | my friend can use it at the shop or in game | Usability | Friend receives my VC and is added to his account | 0 | Ryland | Open
S9 | Friend Editing - remove | S7 | 2 | High | Player | to be able to remove unwanted friends | I can properly manage my "friends" | Usability | Friend is successfully deleted from the friends list | 0 | Ryland | Open
S22 | Message Admin | S14, S15 | 5 | Medium | Admin | to be able to check on players chat logs | Admin can check for any profanity or harassment in the chats | Security | Admin can check to see every registered players chat logs | 0 | Ryland | Open
S25 | Betting | S17-S20 | 3 | Low | Player | to be able to bet Bui's hotel credits each game of Go Fish | I can then use these credits at the hotel (potential prizes feature) | Performance | Users can bet hotel credits before each game of Go Fish | 0 | Ryland | Open
S13 | Change Icons | S12 | 1 | Medium | Player | to be able to change my player icon | I can express myself though cool icons! | Usability | I can successfully change my icon to the one i want | 0 | Silas/Marley | Open
S27 | Ask | S17-S20 | 8 | High | Player | to be able to ask other players if they have a specific rank im looking for | I can either add those cards to my deck, or Go Fish in the middle of the board | Usability | A player can ask any current player for a specific rank. If not, they Go Fish | 0 | Silas | Open
S16 | Tutorial | S5 | 3 | Low | Player | to be able to be trained by a tutorial bot | I can learn how to play Go Fish | Performance: Computer that teaches the player shouldn't be too difficult | Players understand how the game works | 2 | Silas | Open
S1 | User Account |  | 2 | High | Player | to create an account | I can save my data/stats from playing Go Fish | Usability | When a player registers a new account and their info gets saved | 1 | Silas | Open
S5 | HUB / Menu |  | 3 | High | Player | to have a menu where i can choose to create/join lobbies, message people, manage friends, and play a tutorial | I can easily access my key features | Usability | A player has a menu where they can choose what they want to do | 0 | Silas | Open
S6 | Virtual Currency |  | 2 | Medium | Player | to be able to obtain currency from Go Fish games | I can make wagers or purchase other things in the hotel | Usability | When players gain or lose virtual currency based on whether they win or lose a game | 0 | Silas | Open
S12 | Shop | S5, S6 | 3 | Medium | Player | access to the shop in my main menu | I can purchase new icons or other cosmetics | Usability | I can successfully purchase new icons to add to my user | 0 | Marley | Open
S24 | Game Queue Up | S17-S20 | 1 | High | Player | to be able to queue up when im ready to start the game | I can start playing when me + everyone else is ready | Performance | Once everyone queues up the game begins | 0 | Silas | Open
S14 | Private Messaging | S5 | 3 | Medium | Player | to be able to message my friends in private | I can send specific information, such as my lobby code (or theirs) to them | Usability | A player can message people in private 1 on 1 conversation | 0 | Ryland | Open
S15 | Public Messaging | S5 | 3 | Medium | Player | to be able to message the whole lobby | I can interact with others / ask questions if needed | Usability | A player can send a public message the whole lobby can see | 0 | Ryland | Open
S17 | Private Lobby Creation | S5 | 3 | High | Player | to be able to create a private lobby | other players i personally want to invite get join | Usability | A player can generate their own lobby with a login code | 0 | Silas | Open
S18 | Public Lobby Creation | S5 | 3 | High | Player | to be able to create a public lobby | other players can join and play with me | Usability | A player can generate their own lobby for users to join | 0 | Silas | Open
S7 | Adding a Friend |  | 2 | High | Player | to be able to enter the username of the friend i want to add | I can have easier access to them (messaging, inviting, etc) | Usability | The invitiation is sent to the friend / after accepting, they are added to list | 0 | Ryland | Open
S19 | Joining a Private Lobby | S5 | 3 | High | Player | to be able to join a lobby based on a login code | I can play with my friends online | Usability | A player can join their friends in a password-specific lobby | 0 | Silas | Open
S20 | Joining a Public Lobby | S5 | 3 | High | Player | to be able to join a open lobby | I can play with other players online | Usability | A player can join a public open lobby | 0 | Silas | Open
S8 | Friend Requests | S7 | 3 | High | Player | to see who has previously requested to be my friend | I can accept / decline new requests i have | Usability | The player can accept / reject players friend requests | 0 | Ryland | Open
S26 | View Cards | S17-S20 | 2 | High | Player | to be able to check all the cards i currently have in my desk | I can see what move I need to make next | Usability | A player can check to see what cards they have | 0 | Silas | Open
Pending Acceptance Stories
S21 | Admin (epic makes more sense here) | S3 | 5 | High | Admin | to manage other players | Games are being ran smoothly | Security: Permission to enter the game | When an admin can spectate and makes changes to the players at any given time; Not restricted to turns like players | 0 | Ryland | Open
S23 | Admin Bans |  | 5 | Low | Admin | to be able to ban players who are misbehaving | I can ensure the safety of others | Security | Misbehaving players are banned, meaning they cant log in anymore (its probably really difficult | 0 | Ryland | Open
S28 | Wins/Losses | S1 | 1 | Low | Player | to be able to see my overall wins and losses | I can compare my record with other players | Usability | When I can see the total wins and losses on my account | 1 | Silas | Open